## Sheet1
NUMERACY DAY PLANNING SCHEDULE | Toolkit downloads | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
ACTIVITY
PLANNING
Obtain buy-in from colleagues on the idea of the day - emails/meeting to discuss purpose and objectives | https://www.dropbox.com/sh/lcfsxb225v0v91z/AADyCatFiM0q1b6F9BNRkNKCa?dl=0
Agree on date and type of campaign (1 day or a week-long celebration)
Download National Numeracy toolkit items - logo, posters, digital banners, template campaign narrative, explanation of the Challenge online, template social media posts, images | https://www.dropbox.com/home/Numeracy%20Day%20Toolkit%20for%20Colleges
National Numeracy Logos | https://www.dropbox.com/sh/lpxmeqemj6q2rlo/AAAf0WCeoGJ9_I5TG-5vXIMta?dl=0
Digital banners & buttons | https://www.dropbox.com/sh/e1ubacm0tpfb4j6/AAB14Ukj_osKQo0j-tPRmT8xa?dl=0
Posters | https://www.dropbox.com/sh/dqa782fphleh7y5/AAAxcJSHZvTTkYq0T0d0I5dQa?dl=0
Leaflets | https://www.dropbox.com/sh/49l4076obusmamx/AAB1zMfC-5QxHxnGyXtkt77ga?dl=0
Comms guide, Email templates | https://www.dropbox.com/sh/s9aci3rs2b125qk/AABm60w-68Hm7PEU64q-Cm8Na?dl=0
Template tweets | https://www.dropbox.com/sh/uuzb9oxe5situzp/AADrYK-4N86Qg_6TpdJS8dC3a?dl=0
Images | https://www.dropbox.com/sh/ef2r3vplq20uglc/AAAtyywOuCH0qG7LtvGdDicsa?dl=0
Discussion topics for lessons | https://www.dropbox.com/sh/140isauhav5u3i9/AAA-MHY59JqCuSvSP48xWftja?dl=0
A walk through of the Challenge for Staff | https://www.dropbox.com/sh/lcfsxb225v0v91z/AADyCatFiM0q1b6F9BNRkNKCa?dl=0
Plan dates for reminder communications before the event, announcement on go-live date and post-event follow-up
Events
Events planning e.g. - Venue sourcing and management if holding dedicated numbers workshops or group activities
Obtain commitment from all staff to check with their classes that students have at least registered on the Challenge website and started the assessment (be prepared to reiterate that numbers and data are used in most courses and careers!) www.nnchallenge.org.uk
Prepare printing for events
Run XX events
CONTENT
Create 'save the date' comms such as website news item, email to staff and students & include in newsletters or announcements to parents. use National Numeracy logo, banner and badge | https://www.dropbox.com/sh/s9aci3rs2b125qk/AABm60w-68Hm7PEU64q-Cm8Na?dl=0
Create launch news items, email comms
Create 'thank you for taking part' news item, email comms
Send 'save the date' comms 6-8 weeks ahead of campaign
Social media
Create series of posts for pre-launch as teasers, go-live and follow-up 'thanks for taking part/we took part' | https://www.dropbox.com/sh/uuzb9oxe5situzp/AADrYK-4N86Qg_6TpdJS8dC3a?dl=0
Plot posts into calendar each week
Prepare to be reactive on social media
GO LIVE NUMERACY DAY!
Launch go-live news item & social media posts & send go-live comms via email - encourage people to take the NN Challenge
Put up National Numeracy posters to promote the event | https://www.dropbox.com/sh/dqa782fphleh7y5/AAAxcJSHZvTTkYq0T0d0I5dQa?dl=0
Post NND
Follow up and thank you email and social media posts